## Worksheet
No. | Action | Duration (h) | Window (h) | U10 limit (m s−1) | Hs limit (m)
1 | Load technicians and components at port | 4 | – | – | –
2 | SSCV transits to site | Distance/vessel speed | – | 15 | 4.5
3 | Turn off turbine | – | – | – | –
4 | Position and prepare for lift | 4 | Yes | 15 | 3.5
5 | Major component replacement | Depends on failure | – | 15 | 3.5
6 | Recover positioning and secure crane | 4 | Yes | 15 | 3.5
7 | Turn on turbine | – | – | – | –
8 | SSCV transits to port | Distance/vessel speed | – | 15 | 4.5
9 | Unload technicians and components at port | 4 | – | – | –